## Projects
Nome progetto | Acronimo | Ente finanziatore | Start date | End date
| SHIFT | EU Horizon Europe
| SOIL | EU Horizon Europe
| IoTLINK | ESA
| Diplexer | ESA
RECONFIGURABLE ANTENNAS FOR MOBILE TERMINALS BASED ON ACTIVE ACTUATORS | Cascaded | ESA | 2025-04-15
| SpaceITUP | PNRR
| Antenna on Chip | Internal
| CNR Leonardo | CNR | 2025-06-02 | 2025-10-20
Circularly polarized ESPAR | CP-ESPAR | Internal
| Cascade call Restart | PNRR |  | 2025-10-31
| NXP - Near Field antenna | NXP
| Printed Phase shifter | Internal
Single Cell Biosensor | Biosensor | Internal
| 200 GHz Doppler Radar | CHIPS IT - UNICAL - UNIPV | 2025-11-01

## Tasks
Project | Task name | Task owner | Task supervisor | Task status | Expected deadline | Completion date | Short notes | Extended notes (link)
SOIL | CMOS beamformer matrix | Luigi Boccia | Luigi Boccia | Planned | 2026-03-31 |  |  | SOIL - CMOS beamformer matrix
SOIL | COS LNA | Luigi Boccia | Luigi Boccia | Planned | 2026-03-31
Cascaded | Reconfigurable TA | Raffaele De Marco | Luigi Boccia | Working on
Cascaded | ESACA | Raffaele De Marco | Luigi Boccia | Working on
SOIL | Butler matrix | Arman Bordbar | Luigi Boccia | Working on
Antenna on Chip | Antenna on chip | Luigi Boccia | Luigi Boccia | Working on
SHIFT | Antenna | Emilio Arnieri | Emilio Arnieri | Working on
CP-ESPAR | CP-ESPAR | Raffaele De Marco | Raffaele De Marco | Working on
SHIFT | Mixer simulation | Oscar Sciallis | Luigi Boccia | Working on | 2026-01-31 |  |  | SHIFT - Mixer simulation
Cascade call Restart | Magnetolectric dipole design | G. Amendola | G. Amendola | Working on
NXP - Near Field antenna | Near field antenna design | Emilio Arnieri | Emilio Arnieri | Working on
Printed Phase shifter | New Prototype layout | Ehsan Afkari | Luigi Boccia | Not started | 2026-01-31 |  | Finalize new layout, review together and place order.
Biosensor | Single cell biosensor prototype | Antonio Alati | Luigi Boccia | Working on
SHIFT | Board per test mixer | Oscar Sciallis | Luigi Boccia | Working on | 2026-01-21 |  | Verificare chi se ne sta occupando.
200 GHz Doppler Radar | Define roadmap | Giuseppe Sansevero | Luigi Boccia | Working on | 2026-06-27 |  |  | 200 GHz Doppler Radar - Define roadmap
SHIFT | Test-board for the Vector Modulator and gain stage | Luigi Boccia | Melih Gökdemir | Not started | 2026-01-31 |  |  | SHIFT - Test-board for the Vector Modulator and gain stage
SpaceITUP | RF front end | Arman Bordbar | G. Amendola | Working on
Cascade call Restart | Converter design | Mohammed Alramadan | G. Amendola | Working on
IoTLINK | IoT link antnenna optimization | Raffaele De Marco | G. Amendola | Working on
SOIL | PCB design for the mixer tests | Luigi Boccia | Oscar Sciallis | Not started | 2026-01-20
SOIL | LNA strutturato | Oscar Sciallis | Oscar Sciallis | Working on |  |  |  | SOIL - LNA strutturato

## SubTasks
Project | Task name | Sub-task name | Sub-Task owner | Subtask supervisor | Sub-Task status | Deadline | Completion date | Short notes | Extended notes (link) | Colonna 1 | Colonna 2 | Colonna 3 | Colonna 4 | Colonna 5 | Colonna 6 | Colonna 7 | Colonna 8 | Colonna 9 | Colonna 10 | Colonna 11 | Colonna 12 | Colonna 13 | Colonna 14 | Colonna 15 | Colonna 16 | Colonna 17 | Colonna 18
Cascaded | ESACA | NGD chip | Ehsan Afkari |  | Working on |  |  |  | Cascaded - NGD chip
SHIFT | Butler matrix | Chip measurement | Arman Bordbar | Luigi Boccia | Not started | 2026-02-04 |  | To be measured in Grenoble. Arman prepares measurement test-set up
Antenna on Chip | Antenna on chip | Measure radiation patterns | Luigi Boccia |  | Planned
Cascaded | Reconfigurable TA | RTA PCB layout finalization | Raffaele De Marco | Luigi Boccia | Working on
Cascaded | Reconfigurable TA | Unit-cell validation | Raffaele De Marco | Luigi Boccia | Not started
CP-ESPAR | CP-ESPAR | Design finalization | Mohammed Alramadan | Raffaele De Marco | Working on
Antenna on Chip | Antenna on chip | Simulation | Mohammed Alramadan | Raffaele De Marco | Working on
IoTLINK | Antenna design | Antenna optimization | Mohammed Alramadan | Raffaele De Marco | Working on
Cascade call Restart |  | Antenna design | Mohammed Alramadan | Raffaele De Marco | Working on |  |  | first prototype sent for fabrication
NXP - Near Field antenna | Near field antenna design | Antenna design | Gabriel Parreno | Emilio Arnieri | Working on
Cascaded | ESACA | NGD printed circuit | Ehsan Afkari | Raffaele De Marco | Completed |  | 2026-02-06 17:30
SOIL | CMOS beamformer matrix | Hybrid coupler layout: RUN1 | Ehsan Afkari | Luigi Boccia | Completed | 2026-01-16 | 2026-02-06 17:29 | Identify stack-up. Run EMX simulations.
SOIL | CMOS beamformer matrix | Absorptive Switch: RUN1 | Ehsan Afkari | Luigi Boccia | Completed | 2026-01-16 | 2026-02-06 17:29
200 GHz Doppler Radar | Define roadmap | Bibliographic reserach on G-band architecture | Giuseppe Sansevero | Luigi Boccia | Completed | 2026-01-10 | 2026-01-20 11:05 |  | 200 GHz Doppler Radar - Ricerca bibliografica architetture > 150 GHz
SOIL | COS LNA | Layout check: Run 1 | Oscar Sciallis | Luigi Boccia | Blocked | 2026-01-16 |  | Data run non presente su https://cime-p.cime.grenoble-inp.fr/technologies/run-schedule
200 GHz Doppler Radar | Define roadmap | Study of Cadence design systems | Giuseppe Sansevero | Luigi Boccia | Not started | 2026-06-27
SHIFT | Mixer simulation | Contattare Pavia per interfaccia MIXER DAC | Oscar Sciallis | Luigi Boccia | Completed | 2026-03-10 | 2026-03-12 | Urgentissimo | SHIFT - Contattare Pavia per interfaccia MIXER DAC
SHIFT | Mixer simulation | Finalizzare simulazione | Oscar Sciallis | Luigi Boccia | Working on | 2026-03-13 |  | Urgentissimo | SHIFT - Finalizzare simulazione
SHIFT | Mixer simulation | TX Schematic that can pass LVS | Oscar Sciallis | Luigi Boccia | Working on |  |  |  | SHIFT - TX Schematic that can pass LVS
SHIFT | Mixer simulation | Interfaccia MIXER DAC | Oscar Sciallis | Luigi Boccia | Working on | 2026-03-18 |  | Waiting for Antonio Aprile testbench

## Data
People | Task status | E-mail addresses
Luigi Boccia | Not started | luigi.boccia@unical.it
G. Amendola | Planned | g.amendola@unical.it
Emilio Arnieri | Working on | emilio.arnieri@unical.it
Francesco Greco | Blocked | f.greco@dimes.unical.it
Ehsan Afkari | Completed | ehsan.afkari@dimes.unical.it
Antonio Alati | Cancelled | antonio.alati@dimes.unical.it
Mohammed Alramadan | Manufacturing | mohammed.alramadan@dimes.unical.it
Raffaele De Marco |  | raffaele.demarco@dimes.unical.it
Arman Bordbar |  | arman.bordbar@dimes.unical.it
Melih Gökdemir |  | melih.gokdemir@dimes.unical.it
Javad Tavakoli |  | javad.tavakoli@dimes.unical.it
Gabriel Parreno |  | gabriel.parreno@dimes.unical.it
Oscar Sciallis |  | oscar.sciallis@dimes.unical.it
Giuseppe Sansevero |  | g.sansevero@dimes.unical.it
Mattia Di Cianni

## Archivio Tasks
Project | Task name | Task owner | Task status | Expected deadline | Completion date | Short notes | Extended notes (link)
CNR Leonardo | Progettazione sensori su pannello fibra carb | Luigi Boccia | Luigi Boccia | Completed | 2025-10-20 | 2025-11-12 10:29 |  | CNR Leonardo - Progettazione sensori su pannello fibra c
SHIFT | Check the layout - DC pad connections | Luigi Boccia | Melih Gökdemir | Completed | 2026-02-02 | 2026-02-04 12:29 | Very urgent
SHIFT | Layout combinato con Phase shifters | Oscar Sciallis | Luigi Boccia | Completed | 2025-12-01 | 2025-12-19 15:13 |  | SHIFT - Layout combinato con Phase shifters
SOIL | Single slide presentation for the LNA | Oscar Sciallis | Luigi Boccia | Completed | 2025-11-20 | 2025-12-19 15:13 |  | SOIL - Single slide presentation for the LNA
SOIL | Single Slide describing the layout of the Butler matrix | Ehsan Afkari | Luigi Boccia | Completed | 2025-11-19 | 2026-02-05 17:27 | Show in a single slide the requirements, the high level design and the different blocks of the Butler matrix and switch
SOIL | Rispondere ai commenti CIME CMP per sim CMOS | Oscar Sciallis | Luigi Boccia | Completed | 2025-10-27 | 2025-11-12 11:00

## Archivio SubTasks
Project | Task name | Sub-task name | Sub-Task owner | Sub-Task status | Deadline | Completion date | Short notes | Extended notes (link)
| test 23 | test testsub | G. Amendola | Completed | 2025-09-19
SHIFT | test |  |  | Completed
SOIL | CMOS beamformer matrix | Identify configuration | Arman Bordbar | Completed | 2025-09-26 | 2025-09-26 17:25 | Identify Butler matrix
SOIL | CMOS beamformer matrix | Define area and book it | Arman Bordbar | Luigi Boccia | Completed | 2025-10-01 | 2025-11-12 10:30
CNR Leonardo | Progettazione sensori su pannello fibra c | Progettazione preliminare | Antonio Alati | Luigi Boccia | Completed | 2025-09-29 | 2025-11-12 10:30 | Rivedere progettazione: 1) sensore patch definito; 2) idea sensore spirale; 3) idea sample caratterizzazione | CNR Leonardo - Progettazione preliminare

## ReadMe
MAIC LAB Task Manager - Quick Start Guide
This tool automates the management and monitoring of activities for MAIC LAB projects directly from Google Sheets.
Subtask creation: a) select a project; b) wait a second so that the Task cell is populated; c) select the main Task list which will appear. In case of error, cancel the Project and start over.
"MAIC LAB" Menu
All main functions are accessible from the "MAIC LAB" menu that appears when the file is opened.
📝 Create Extended Notes for Selected Row (Task or sub-task)
What it does: Creates an extended notes document for a task or sub-task.
How to use it: Select the row (just by placing the cursor on a cell in the row) of a task (in the Tasks sheet) or a sub-task (in the SubTasks sheet) and click this menu item. The script will create a Google Doc, populate it with the data from the row, and insert the link into the "Extended notes" column.
📄 Reporting and Monitoring
This submenu allows you to generate 3 types of reports in Google Docs format. The report files have fixed names and are overwritten each time they are run to maintain stable sharing links.
Global Activity Report: A document with all ongoing activities, grouped by project.
Report by Person (Complete): A document with all activities, grouped by the responsible person (owner).
Report for a Single Person: Opens a dialog box to select a specific person and generate a report dedicated solely to their activities.
🗄️ Archive Completed Tasks/Sub-tasks
What it does: Cleans up the active worksheets by moving completed activities.
How to use it: Use the two separate menu items to move tasks or sub-tasks with a "Completed" or "Cancelled" status to their respective archive sheets (Archivio Tasks, Archivio SubTasks). The associated notes files are also archived (moved to the trash).